## 1.Client Information
Product Name |  | Shapla City CRM |  | Table no - 1 | CRM Start Date | 25/10/2022 | CRM End Date | 25/10/2022 | Page Name: Client Information |  |  | Page Number - 2
Feature ID | Modual Name | Frontend Design (FD) | FD- Time | Task Design(TD) | TD- Time | Action Type | Output | Remark/Assign By | Developer Time | Report Time | Date | Total Time | Developer want time
F1 | Client Information | HTML + CSS + Text | 1 min | A text will appear at the left-middle of the page | 2 min | text value | A text will appear at the left-middle of the page |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
F2 | Copy | HTML + CSS + Text | 4 min | When We click on it the current page copy as a page | 10 min | Clickable | A new page will open as a page |  | 4 min | 2 min |  | (4+10+4+2) min = 20 min
F3 | Print | HTML + CSS + Text | 4 min | When we click on it the current page will appean as a printable view | 10 min | Clickable | current page will ready as a page to print |  | 4 min | 2 min |  | (4+10+4+2) min = 20 min
F4 | PDF | HTML + CSS + Text | 4 min | When we click on it the current page will ready as PDF formate which is downloadable | 10 min | Clickable | current page will ready as a PDF view and downloadable option will exists |  | 4 min | 2 min |  | (4+10+4+2) min = 20 min
F5 | Add customer | CSS + Color + text | 5 min | When we click it new page will open | 8 min | Clickable | A new page will open |  | 4 min | 3 min |  | (5+8+4+3) min = 20 min
F6 | Search bar | CSS + Color + text | 5 min | When we click on it ,it will appear as a writable mode, we can search here by meme & id etc, when we comite a suggetion list will shown in below | 10 min | writeable , Clickable | we can write on this boz, a suggestion list will shown in bellow |  | 5 min | 2 min |  | (5+10+5+2) min = 22 min
F7 | 14 column(8 column is viweable and others 6 column is clickable) | HTML + CSS + Text | 15 min | here date & customer name is sortable, customer mobile no is clickable, contact customer, details update view, extra Documents columns are also clickable & others are viewable | 9*2 = 18 min 4*15 = 60 min 1*20 = 20 min Total = 100 min | viewable , Clickable | 1. when we click on clickable 5 column listed below things will happen 2. Phone number column will create a calling environment 3. Contact customer column 2 icon will clickable and link to messenger & whatsapp 4. Edit icon will clickable 5. view icon also clickable link a new page |  | 1*14 = 14 min + 6 min Total = 20 min | 15 min |  | (15+100+20+15) min = 150 min = 2.5 hour
F8 | Pagenation | HTML + CSS + Text | 2 min | Pagenation page will change clicking on number 1 to 5 member will shown at a time, left & right navigation will use to navigate number by one click 1 number will shift right or left | 8 min | Clickable | Page will clickable , 5 number will appear at a time with left and right icon, click on icon number will shift 1 respectively |  | 5 min | 5 min |  | (2+8+5+5) min = 20 min
[11 empty] | Total Time = | = 4 hour 35 min

## 2.Add Client
Product Name |  | Shapla City CRM |  | Table no - 3 | CRM Start Date | 24/09/2022 | CRM End Date |  | Page Name: Add Client (4) |  |  | Page Number - 2A
Feature ID | Modual Name | Frontend Design (FD) | FD- Time | Task Design(TD) | TD- Time | Action Type | Output | Remark/Assign By | Developer Time | Report Time | Date | Total Time | Developer want time
F1 | Add Client | HTML + CSS + Text | 1 min | A text will appear at the left-middle of the page | 2 min | text value | A text will appear at the left-middle of the page |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
F2 | File No. | HTML + CSS + Text | 2 min | File no will auto generate or writeable | 4 min | writeable\Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F3 | Customer Name 1 | HTML + CSS + Text | 2 min | This file will writable | 4 min | writeable | when user click on this box it will create a writable environment. Its a mandatory field |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F4 | Customer ID | HTML + CSS + Text | 2 min | File no will auto generate or writeable | 4 min | writeable\Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F5 | Father's Name | HTML + CSS + Text | 2 min | This file will writable | 4 min | writeable | when user click on this box it will appear as a writable state |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F6 | Mother's Name | HTML + CSS + Text | 2 min | This file will writable | 4 min | writeable | when user click on this box it will appear as a writable state |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F7 | Husband / Wife name | HTML + CSS + Text | 2 min | Husband / Wife name will written in this box (check box option) | 10 min | writeable | when user click on this box it will appear as a writable state a checkbox will here for define relationship |  | 5 min | 2 min |  | (2+10+5+2) min = 19 min ~ 20 min
F8 | National ID Number | HTML + CSS + Text | 2 min | This seation will be a input field, validation needed | 15 min | writeable | when user click on this box it will create a writable environment as input field . Its a mandatory field |  | 5 min | 5 min |  | (2+15+5+5) min = 27 min ~ 30 min
F9 | Date of Birth | HTML + CSS + Text | 2 min | Its a input field | 8 min | input date | Here a calender icon will use for date input DD-MM-YY formate . Its a mandatory field |  | 2 min | 2 min |  | (2+8+2+2) min = 14 min ~ 15 min
F10 | Phone no. | HTML + CSS + Text | 2 min | Its a input field. Valid phone number will written here | 10 min | writeable | Here phone number will validate with country code with sign, its a input field. Its a mandatory field |  | 2 min | 2 min |  | (2+10+2+2) min = 16 min ~ 20 min
F11 | Others file no | HTML + CSS + Text | 5 min | Its a input field | 5 min | writeable | Here file no will appear as a writable input file |  | 2 min | 2 min |  | (5+5+2+2) min = 14 min ~ 15 min
F12 | Customer Name 2 | HTML + CSS + Text | 2 min | This file will writable | 4 min | writeable | when user click on this box it will create a writable environment. Its a mandatory field |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F13 | Father's Name | HTML + CSS + Text | 2 min | This file will writable | 4 min | writeable | when user click on this box it will appear as a writable state |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F14 | Booking Date | HTML + CSS + Text | 5 min | Its a input field | 8 min | input date | Here a calender icon will use for date input DD-MM-YY formate. Its a mandatory field |  | 2 min | 2 min |  | (5+8+2+2) min = 15 min
F15 | Profession | HTML + CSS + Text | 2 min | Its a input field | 4 min | writeable | Its a input field. Its a mandatory field |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F16 | Designation(optional) | HTML + CSS + Text | 2 min | Its a input field | 4 min | writeable | Its a input field but not mandatory |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F17 | Email Address | HTML + CSS + Text | 2 min | Its a input field | 8 min | writeable | Its a input field validation needed. Its a mandatory field |  | 3 min | 2 min |  | (2+8+3+2) min = 15 min
F18 | Mailing Address | HTML + CSS + Text | 2 min | Its a input field | 4 min | writeable | Its a input field, |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F19 | Permanent Address | HTML + CSS + Text | 2 min | Its a input field | 4 min | writeable | Its a input field . Its a mandatory field |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F20 | Office Address (Optional) | HTML + CSS + Text | 2 min | Its a input field | 4 min | writeable | Its a input field but not mandatory |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F21 | Country | HTML + CSS + Text | 5 min | its a field dropdown | 5 min | selectable | input field from dropdown input field & mandatory field |  | 2 min | 2 min |  | (5+5+2+2) min = 15 min
F22 | Nominee | HTML + CSS + Text | 2 min | Its a input field | 5 min | writeable | Its a input field also a mandatory field |  | 2 min | 2 min |  | (2+5+2+2) min = 11 min ~ 15 min
F23 | Relation with Nominee | HTML + CSS + Text | 2 min | Its a input field | 5 min | writeable | Its a input field also a mandatory field |  | 2 min | 2 min |  | (2+5+2+2) min = 11 min ~ 15 min
F24 | Nominee contact number | HTML + CSS + Text | 2 min | Its a input field.with country code with + sign | 5 min | writeable | Contact number will input as number with country code & sign validation needed. Its a mandatory field |  | 2 min | 2 min |  | (2+5+2+2) min = 11 min ~ 15 min
F25 | Nominee address | HTML + CSS + Text | 2 min | Its a input field | 5 min | writeable | Its a input field also. Its a mandatory field |  | 2 min | 2 min |  | (2+5+2+2) min = 11 min ~ 15 min
F26 | Nominee gets | HTML + CSS + Text | 2 min | Its a input field | 5 min | writeable | Its a input field also. Its a mandatory field |  | 2 min | 2 min |  | (2+5+2+2) min = 11 min ~ 15 min
F27 | Building no | HTML + CSS + Text | 2 min | File no will auto generate or writeable | 4 min | writeable\Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F28 | Flat No | HTML + CSS + Text | 5 min | Its a input field select from dropdown | 5 min | selectable | A dropdown list will appear & field will fill from that dropdown |  | 2 min | 2 min |  | (5+5+2+2) min = 14 min ~ 15 min
F29 | Flat Size | HTML + CSS + Text | 5 min | Its a selectable field from dropdown | 5 min | selectable | A dropdown list will appear & field will fill from that dropdown. Its a mandatory field |  | 2 min | 2 min |  | (5+5+2+2) min = 14 min ~ 15 min
F30 | Media Name | HTML + CSS + Text | 2 min | Its a input field | 2 min | writeable | Its a input field, Its a mandatory field |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F31 | Media Phone number | HTML + CSS + Text | 2 min | Its a input field | 2 min | writeable | Its a input field ,validation needed. Its a mandatory field |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F32 | Client's Image | HTML + CSS + Text | 5 min | Its a input field | 5 min | on change | Its a input field ,JPG type will only allowed here. Its a mandatory field |  | 2 min | 2 min |  | (5+5+2+2) min = 14 min ~ 15 min
F33 | Nominee's Image | HTML + CSS + Text | 5 min | Its a input field | 5 min | on change | Its a input field ,JPG type will only allowed here. Its a mandatory field |  | 2 min | 2 min |  | (5+5+2+2) min = 14 min ~ 15 min
F34 | Agreement Upload(multiple) | HTML + CSS + Text | 5 min | Its a input field | 5 min | on change | Its a input field ,JPG docs,excel &pdf multiple file can upload here. Its a mandatory field |  | 3 min | 2 min |  | (5+5+3+2) min = 15 min
F35 | Submit | HTML + CSS + Text | 5 min | its a button for from submit | 5 min | Clickable | its a clickable button for from submit. Its a mandatory field |  | 2 min | 2 min |  | (5+5+2+2) min = 14 min ~ 15 min
[11 empty] | Total Time = | = 7 hours and 35 minutes

## 3.Add Client (UpdateEdit Page)
Product Name |  | Shapla City CRM |  | Table no - 4 | CRM Start Date | 24/09/2022 | CRM End Date |  | Page Name: Add Client (Update/Edit Page) |  |  | Page Number - 2B
Feature ID | Modual Name | Frontend Design (FD) | FD- Time | Task Design(TD) | TD- Time | Action Type | Output | Remark/Assign By | Developer Time | Report Time | Date | Total Time | Developer want time
F1 | Update Client | HTML + CSS + Text | 1 min | A text will appear at the left-middle of the page | 2 min | text value | A text will appear at the left-middle of the page |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
F2 | File No. | HTML + CSS + Text | 1 min | File no will auto generate or writeable | 2 min | writeable / auto fill | Its a input field validation needed |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
F3 | Customer Name 1 | HTML + CSS + Text | 2 min | File no will auto generate | 4 min | Data fetch & inchange | when user click on this box it will create a writable environment |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F4 | Customer ID | HTML + CSS + Text | 2 min | File no will auto generate | 4 min | Data fetch & inchange | when user click on this box it will create a writable environment |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F5 | Father's Name | HTML + CSS + Text | 2 min | This file will writable | 4 min | Data fetch & inchange | when user click on this box it will appear as a writable state |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F6 | Mother's Name | HTML + CSS + Text | 2 min | This file will writable | 4 min | Data fetch & inchange | when user click on this box it will appear as a writable state |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F7 | Husband / Wife name | HTML + CSS + Text | 2 min | Husband / Wife name will written in this box (check box option) | 2 min | Data fetch & inchange | when user click on this box it will appear as a writable state a checkbox will here for define relationship |  | 4 min | 2 min |  | (2+2+4+2) min = 10 min
F8 | National ID Number | HTML + CSS + Text | 2 min | This seation will be a input field, validation needed | 5 min | Data fetch & inchange | when user click on this box it will create a writable environment as input field , its a mandatory field |  | 5 min | 5 min |  | (2+5+5+5) min = 17 min ~ 20 min
F9 | Date of Birth | HTML + CSS + Text | 5 min | Its a input field | 0 min | Data fetch & inchange | Here a calender icon will use for date input DD-MM-YY formate mandatory field |  | 2 min | 2 min |  | (5+0+2+2) min = 14 min ~ 15 min
F10 | Phone no. | HTML + CSS + Text | 2 min | Its a input field. Valid phone number will written here | 5 min | Data fetch & inchange | Here phone number will validate with country code with sign, its a input field, mandatory field |  | 2 min | 2 min |  | (2+5+2+2) min = 11 min ~ 20 min
F11 | Others file no | HTML + CSS + Text | 5 min | Its a input field | 5 min | Data fetch & inchange | Here file no will appear as a writable input file |  | 2 min | 2 min |  | (5+5+2+2) min = 14 min ~ 15 min
F12 | Customer Name 2 | HTML + CSS + Text | 2 min | This file will writable | 4 min | Data fetch & inchange | when user click on this box it will create a writable environment |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F13 | Father's Name | HTML + CSS + Text | 2 min | This file will writable | 4 min | Data fetch & inchange | when user click on this box it will appear as a writable state |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F14 | Booking Date | HTML + CSS + Text | 5 min | Its a input field | 1 min | Data fetch & inchange | Here a calender icon will use for date input DD-MM-YY formate |  | 2 min | 2 min |  | (5+1+2+2) min = 10 min
F15 | Profession | HTML + CSS + Text | 2 min | Its a input field | 4 min | Data fetch & inchange | Its a input field |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F16 | Designation(optional) | HTML + CSS + Text | 2 min | Its a input field | 2 min | Data fetch & inchange | Its a input field but not mandatory |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F17 | Email Address | HTML + CSS + Text | 2 min | Its a input field | 2 min | Data fetch & inchange | Its a input field validation needed |  | 3 min | 2 min |  | (2+2+3+2) min = 9 min ~ 10 min
F18 | Mailing Address | HTML + CSS + Text | 2 min | Its a input field | 2 min | Data fetch & inchange | Its a input field also a mandatory field |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F19 | Permanent Address | HTML + CSS + Text | 2 min | Its a input field | 2 min | Data fetch & inchange | Its a input field also a mandatory field |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F20 | Office Address (Optional) | HTML + CSS + Text | 2 min | Its a input field | 2 min | Data fetch & inchange | Its a input field but not mandatory |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F21 | Country | HTML + CSS + Text | 2 min | its a field dropdown | 2 min | Data fetch & inchange | input field from dropdown input field & mandatory field |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F22 | Nominee Name | HTML + CSS + Text | 2 min | Its a input field | 2 min | Data fetch & inchange | Its a input field also a mandatory field |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F23 | Relation with Nominee | HTML + CSS + Text | 2 min | Its a input field | 2 min | Data fetch & inchange | Its a input field also a mandatory field |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F24 | Nominee contact number | HTML + CSS + Text | 2 min | Its a input field.with country code with + sign | 2 min | Data fetch & inchange | Contact number will input as number with country code & sign validation needed |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F25 | Nominee address | HTML + CSS + Text | 2 min | Its a input field | 2 min | Data fetch & inchange | Its a input field also |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F26 | Nominee gets | HTML + CSS + Text | 2 min | Its a input field | 2 min | Data fetch & inchange | Its a input field also |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F27 | Building no | HTML + CSS + Text | 2 min | Its a input field | 2 min | Data fetch & inchange | Its a input field also |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F28 | Flat No | HTML + CSS + Text | 2 min | Its a input field select from dropdown | 2 min | Data fetch & inchange | A dropdown list will appear & field will fill from that dropdown |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F29 | Flat Size | HTML + CSS + Text | 2 min | Its a selectable field from dropdown | 2 min | Data fetch & inchange | A dropdown list will appear & field will fill from that dropdown |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F30 | Media Name | HTML + CSS + Text | 2 min | Its a input field | 2 min | Data fetch & inchange | Its a input field |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F31 | Media Phone number | HTML + CSS + Text | 2 min | Its a input field | 2 min | Data fetch & inchange | Its a input field ,validation needed |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F32 | Client's Image | HTML + CSS + Text | 5 min | Its a input field | 5 min | Data fetch & inchange | Its a input field ,JPG type will only allowed here |  | 2 min | 2 min |  | 5+5+2+2) min = 14 min ~ 15 min
F33 | Nominee's Image | HTML + CSS + Text | 5 min | Its a input field | 5 min | Data fetch & inchange | Its a input field ,JPG type will only allowed here |  | 2 min | 2 min |  | 5+5+2+2) min = 14 min ~ 15 min
F34 | Agreement Upload(multiple) | HTML + CSS + Text | 5 min | Its a input field | 5 min | Data fetch & inchange | Its a input field ,JPG docs,excel &pdf multiple file can upload here |  | 2 min | 2 min |  | 5+5+2+2) min = 14 min ~ 15 min
F35 | Update | HTML + CSS + Text | 5 min | its a button for from update | 5 min | Data fetch & inchange | its a clickable button for from update |  | 2 min | 2 min |  | 5+5+2+2) min = 14 min ~ 15 min
[11 empty] | Total Time = | = 390 min = 6 hours and 30 minutes

## 4.View Client Information
Product Name |  | Shapla City CRM |  | Table no - 5 | CRM Start Date | 2022-04-10 | CRM End Date | 2022-08-10 | Page Name: View Customer Page |  |  | Page Number - 2C
Feature ID | Modual Name | Frontend Design (FD) | FD- Time | Task Design(TD) | TD- Time | Action Type | Output | Remark/Assign By | Developer Time | Report Time | Date | Total Time | Developer want time
F1 | View Customer Information | HTML + CSS + Text | 1 min | A text will appear at the left-middle of the page | 2 min | text value | A text will appear at the left-middle of the page |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
F2 | Copy | HTML + CSS + Text | 2 min | When We click on it the current page copy as a page | 4 min | Clickable | A new page will open as a page |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F3 | Print | HTML + CSS + Text | 2 min | When we click on it the current page will appean as a printable view | 4 min | Clickable | current page will ready as a page to print |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F4 | PDF | HTML + CSS + Text | 2 min | When we click on it the current page will ready as PDF formate which is downloadable | 4 min | Clickable | current page will ready as a PDF view and downloadable option will exists |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F5 | Legal paper folder | HTML + CSS + Text | 2 min | When user click on it a new page will open | 4 min | Clickable | current page will change to new page |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F6 | File no Customer ID Building No Flat No Flat size | HTML + CSS + Text | 3 min | all this field will shown with it value at the left side of page in two row | 5 min | Data fetch | Here 5 field will shown with value |  | 5 min | 2 min |  | (3+5+5+2) min = 15 min
F7 | information | HTML + CSS + Text | 1 min | A text will appear at the middle of the page | 2 min | text value | A text will appear at the middle of the page |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
F8 | passport size image | HTML + CSS + Text | 5 min | A file will view here as a image size per defined (450x570) | 5 min | Data fetch | A file will viewable here, that means a passport size JPG image view able here |  | 2 min | 2 min |  | (5+5+2+2) min = 14 min ~ 15 min
F9 | Customer’s Name | HTML + CSS + Text | 2 min | This field will be show the data | 4 min | Data fetch | when user check on this box it will show the Customer name |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F10 | Father’s Name | HTML + CSS + Text | 3 min | This field will be show the data | 4 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (3+4+2+2) min = 11 min ~ 15 min
F11 | Mother’s Name | HTML + CSS + Text | 3 min | This field will be show the data | 4 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (3+4+2+2) min = 11 min ~ 15 min
F12 | Husband’s/Wife’s Name | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 4 min | 2 min |  | (2+2+4+2) min = 10 min
F13 | Customer’s Name 2 | HTML + CSS + Text | 2 min | This field will be show the data | 4 min | Data fetch | when user check on this box it will show the Customer name |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F14 | Father’s Name | HTML + CSS + Text | 3 min | This field will be show the data | 4 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (3+4+2+2) min = 11 min ~ 15 min
F15 | Email Address | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 3 min | 2 min |  | (2+2+3+2) min = 9 min ~ 10 min
F16 | Mailing Address | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F17 | Permanent Address | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F18 | Date of Birth | HTML + CSS + Text | 5 min | This field will be show the data | 0 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (5+0+2+2) min = 14 min ~ 15 min
F19 | Phone Number | HTML + CSS + Text | 2 min | This field will be show the data | 5 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+5+2+2) min = 11 min ~ 20 min
F20 | National ID Number | HTML + CSS + Text | 2 min | This field will be show the data | 5 min | Data fetch | when the user checks on this box it will appear as a data |  | 5 min | 5 min |  | (2+5+5+5) min = 17 min ~ 20 min
F21 | Profession | HTML + CSS + Text | 2 min | This field will be show the data | 4 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F22 | Designation (optional) | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F23 | Country | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F24 | Booking Date | HTML + CSS + Text | 5 min | This field will be show the data | 1 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (5+1+2+2) min = 10 min
F25 | Office Address (optional) | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F26 | Nominee’s Information | HTML + CSS + Text | 1 min | A text will appear at the left side of the page | 2 min | text value | A text will appear at the middle of the page |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
F27 | Nominee’s Name | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F28 | Nominee Gets | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F29 | Nominee Address | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F30 | Passport Size Image | HTML + CSS + Text | 5 min | This field will be show the data | 5 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | 5+5+2+2) min = 14 min ~ 15 min
F31 | Nominee Phone Number | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F32 | Relationship With Nominee | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F33 | Media Information | HTML + CSS + Text | 1 min | A text will appear at the left side of the page | 2 min | text value | A text will appear at the middle of the page |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
F34 | Media Name | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F35 | Other File No. | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F36 | Media Phone Number | HTML + CSS + Text | 2 min | This field will be show the data | 2 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | (2+2+2+2) min = 8 min ~ 10 min
F37 | Customer’s Signature | HTML + CSS + Text | 1 min | A text will appear at the left side of the page | 2 min | text value | A text will appear at the middle of the page |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
F38 | Official Signature | HTML + CSS + Text | 1 min | A text will appear at the left side of the page | 2 min | text value | A text will appear at the middle of the page |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
[11 empty] | Total Time = | = 400 min = 6 hour 45 min

## 5.Legal Paper Folder
|  | Total Time | 15+ 20 + 45 =1 hours and 20 minutes
Product Name |  | Shapla City CRM |  | Table no - 6 | CRM Start Date | 2022-09-10 | CRM End Date | 2022-09-10 | Page Name: Legal Paper Folder |  |  | Page Number - 2D
Feature ID | Modual Name | Frontend Design (FD) | FD- Time | Task Design(TD) | TD- Time | Action Type | Output | Remark/Assign By | Developer Time | Report Time | Date | Total Time | Developer want time
F1 | Legal Paper Folder | HTML + CSS + Text | 1 min | A text will appear at the left-middle of the page | 2 min | text value | A text will appear at the left-middle of the page |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
F2 | Property Paper 1(2C) | HTML + CSS + Text | 2 min | When We click on it the current page will move a page | 4 min | Clickable | A new page will open as a page |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
[11 empty] | Total Time = | = 15 min
Product Name |  | Shapla City CRM |  | Table no - 7 | CRM Start Date | 2022-09-10 | CRM End Date | 2022-09-10 | Page Name: Legal Paper view |  |  | Page Number - 2E
Feature ID | Modual Name | Frontend Design (FD) | FD- Time | Task Design(TD) | TD- Time | Action Type | Output | Remark/Assign By | Developer Time | Report Time | Date | Total Time | Developer want time
F1 | Legal Papers View | HTML + CSS + Text | 1 min | A text will appear at the left-middle of the page | 2 min | text value | A text will appear at the left-middle of the page |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
F2 | Add Legal Paper | HTML + CSS + Text | 2 min | When We click on it the current page pop up as a page | 4 min | Clickable | A new pop up page will open as same page |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F3 | Property Paper 1 | HTML + CSS + Text | 2 min | When We click on it the current page will move a page | 4 min | Clickable | A new page will open as a page |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F4 | Demo image | HTML + CSS + Text | 5 min | This field will be show the data | 5 min | Data fetch | when the user checks on this box it will appear as a data |  | 2 min | 2 min |  | 5+5+2+2) min = 14 min ~ 15 min
F5 | Demo image Download | HTML + CSS + Text | 5 min | This field will be show the data and have a download option | 5 min | Data fetch | Its a input field ,JPG file can download image here |  | 2 min | 2 min |  | 5+5+2+2) min = 14 min ~ 15 min
F6 | Demo image view | HTML + CSS + Text | 1 min | When We click on it the current page will show the demo image | 2 min | Data fetch | Its a input field ,JPG file can download image here |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
[11 empty] | Total Time = | = 20 min
Product Name |  | Shapla City CRM |  | Table no - 8 | CRM Start Date | 2022-09-10 | CRM End Date | 2022-09-10 | Page Name: Legal Paper view |  |  | Page Number - 2F
Feature ID | Modual Name | Frontend Design (FD) | FD- Time | Task Design(TD) | TD- Time | Action Type | Output | Remark/Assign By | Developer Time | Report Time | Date | Total Time | Developer want time
F1 | Upload Legal Paper | HTML + CSS + Text | 1 min | A text will appear at the left-middle of the page | 2 min | text value | A text will appear at the left-middle of the page |  | 1 min | 1 min |  | (1+2+1+1) min = 5 min
F2 | Upload Legal Papers multiple image(2D/1 ) | HTML + CSS + Text | 5 min | Its a input field | 5 min | on change | Its a input field ,JPG docs,excel &pdf multiple file can upload here. |  | 3 min | 2 min |  | (5+5+3+2) min = 15 min
F3 | cross button | HTML + CSS + Text | 2 min | its a cross button for the from | 4 min | Clickable | its a clickable button for cross the page. |  | 2 min | 2 min |  | (2+4+2+2) min = 10 min
F4 | submit button | HTML + CSS + Text | 5 min | its a button for from submit | 5 min | Clickable | its a clickable button for from submit. |  | 2 min | 2 min |  | (5+5+2+2) min = 14 min ~15 min
[11 empty] | Total Time = | = 110 min = 45 min